## RTM
CivicConnect Requirements Traceability Matrix (RTM) - M3 release candidate (live) - v3.0
Req ID | Requirement | Source (Stakeholder) | Priority | Acceptance Criteria | ASR / Quality Driver (new at M2) | Design / Architecture (M2) | Data / Persistence (new at M2) | Design / Interface Decision (new at M2) | Technology Decision (new at M2) | ADR / Change / Risk (new at M2) | Issue / PR (â†’ M3) | Implementation (â†’ M3) | Test / Verification (â†’ M3) | Acceptance / Release Evidence (â†’ M4) | Status | Owner | RC Implementation (app/, M3) | Test Case(s) (Test Plan v1) | Expected Result (M3) | Execution Evidence (M3) | Defect / M3 Status
FR-001 | Submit a new service request with the information needed to action it. | ST-1 | Must | AC-001.1; AC-001.2 | ASR-06 | FE submit page -> entry -> Requests | requests schema: request row, ref ID, status Received; category ID checked through the ReferenceData API, no cross-schema FK | ADR-004 view composition; ADR-006 per-field validation errors | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-001; ADR-004; ADR-006; RSK-008; RSK-019 | Backend and UI branches | Core/Services/RequestService.SubmitAsync; Data/Migrations/001_request.sql; Pages/Requests/Submit.cshtml | Not in CI: Backend RequestServiceTests (Overlong_title_is_refused, Staff_cannot_submit_requests_without_the_permission). Planned in CI | at M4 | Changed (CR-010) | M. Malope with K. Marota | Not in app/ (Backend/ only). Request.Submit domain validation exists; no submit page | UT-05, BB-01, BB-02, IT-01, E2E-01 | Valid request saved with a unique reference ID and status Received; a missing field blocks the save and is flagged; over-limit input rejected without a server error | Not run: blocked by B1 | IN*: blocked (B1, port requester slice)
FR-002 | Categorise the request from a controlled category list (not free text). | ST-1, ST-3 | Must | AC-002.1; AC-002.2 | ASR-04; ASR-06 | FE category select -> entry -> ReferenceData | referencedata schema: category table, retired kept | ADR-004; ADR-006 reference-data endpoint | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006; CR-008; RSK-018 | Backend and UI branches | Core/Services/CategoryService; Data/Migrations/002_category.sql; category select on Pages/Requests/Submit.cshtml | Not in CI: covered indirectly by Backend RequestServiceTests. Planned: category test in CI | at M4 | Changed (CR-010) | M. Malope | Category entity and seed (Domain/ReferenceData/Category.cs); no submit form | UT-02 | Only listed categories accepted; unknown, empty or null category rejected and flagged | Not run: blocked by B1 | IN*: blocked (B1)
FR-003 | View the current status of a submitted request. | ST-1 | Must | AC-003.1; AC-003.2 | ASR-06; ASR-01 | FE status view -> entry -> Requests | requests schema: constrained status, read-only to requesters | ADR-004 read-only status display (resolves C-1) | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-004; conflict C-1; RSK-016 | UI branch | Core/Services/RequestService.GetAsync; Pages/Requests/Details.cshtml; TagHelpers/StatusBadgeTagHelper | Not in CI: Backend StatusRulesTests (Display_text_is_plain_language). Planned: page test for AC-003.2 | at M4 | Changed (CR-010) | M. Malope | Not in app/ | E2E-01 | Owned request shows its status in plain language; no control to change it | Not run: blocked by B1 | IN*: blocked (B1)
FR-004 | View a history/list of own previously submitted requests. | ST-1 | Must | AC-004.1; AC-004.2 | ASR-02; ASR-06 | FE history -> entry -> Requests (scope from Access policy) | requests schema: scoped by requester_id, indexed | ADR-005 server-side ownership scoping; ADR-004 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; NFR-003; RSK-011 | Backend and UI branches | RequestService.ListOwnAsync; Pages/Requests/Index.cshtml; index ix_request_requester | Not in CI: Backend RequestServiceTests scope cases. Planned: negative access test | at M4 | Changed (CR-010) | M. Malope with G. Enright | RequestAccess.MayView requester rule; no history page | UT-04, BB-05, E2E-01 | History lists only the requester's own requests; another requester's request returns not found with no data | UT-04 RequestAccessTests: pending first run on frontend-milestone-3-development. BB-05, E2E-01: not run (B1) | IN*: page blocked (B1)
FR-005 | Search/filter own request history. | ST-1 | Should | AC-005.1 | ASR-04 | FE filter -> entry -> Requests | requests schema: (requester_id, status) index, paging | ADR-004; ADR-006 query parameters | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006 | UI branch | Status filter on Pages/Requests/Index.cshtml; ListOwnAsync paging | Planned: filter and empty state page test | at M4 | Changed (CR-010) | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-006 | Attach supporting information to a request (e.g. a photo). | ST-1, ST-2 | Could | AC-006.1 | ASR-05 (cost/complexity) | Not allocated (deferred) | None | Deferred - no design decision taken | Deferred, storage not selected | PED Scope (Deferred); CR required to re-scope; RSK-003; RSK-018 | at M3 | at M3 | at M3 | at M4 | Candidate - may defer | K. Marota on re-scope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-007 | Receive feedback when a request is accepted, rejected, updated or completed. | ST-1 | Must | AC-007.1; AC-007.2 | ASR-06; ASR-05 | Requests writes feedback with the status change -> entry -> FE | requests schema: feedback item in the same transaction as the status change | ADR-002 same-transaction write; in-app pull only, no push | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; conflict C-4; CR-001; RSK-009; RSK-018 | Backend branch | Core/Services/FeedbackService; Data/Migrations/004_feedback.sql; FeedbackController. No requester screen yet | Not in CI: Backend NoteAndFeedbackTests (Nobody_can_mark_someone_elses_feedback_as_read). Planned: timing check | at M4 | Changed (CR-010) | M. Malope with K. Marota | Not in app/ | E2E-02 | A feedback item with a timestamp appears for the requester after a status change | Not run: blocked by B1 and FR-012 wiring | IN* (stretch): blocked (B1)
FR-008 | View the service requests relevant to authorised staff (staff queue). | ST-2 | Must | AC-008.1; AC-008.2 | ASR-02; ASR-04 | FE staff queue -> entry -> Requests | requests schema: queue indexes (status, category, assigned_to) | ADR-005 policy check per query; ADR-004 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; NFR-006; RSK-011 | Backend and UI branches | RequestService.QueueAsync; Pages/Staff/Queue.cshtml; index ix_request_queue | Not in CI: Backend RequestServiceTests (The_queue_is_closed_to_requesters). Planned in CI | at M4 | Changed (CR-010) | M. Malope with G. Enright | Pages/Staff/Queue.cshtml.cs scoped query; Domain/Access/StaffCategoryScope; AuthorisationPolicy with RequestAccess.MayView; Staff/Details returns 404 outside scope | UT-04, BB-03 | Queue lists only requests in the staff member's categories; opening an out-of-scope request by ID returns 404 with no request data | UT-04 RequestAccessTests: pending first run on frontend-milestone-3-development. BB-03: not run (needs a running RC, B2) | IN: B4 closed by category scope
FR-009 | Search, filter or sort requests using useful criteria. | ST-2 | Must | AC-009.1; AC-009.2 | ASR-04 | FE queue filter and sort -> entry -> Requests | requests schema: indexes, sort whitelist, paging | ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006; NFR-004 | Backend and UI branches | Sort whitelist in RequestService.QueueAsync and RequestRepository; status filter on the queue page | Planned: sort and filter tests | at M4 | Changed (CR-010) | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-010 | View the full details of a request. | ST-2 | Must | AC-010.1 | ASR-02; ASR-03 | FE staff detail -> entry -> Requests | requests schema: request with history and notes | ADR-005; ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; RSK-011 | Backend and UI branches | RequestService.GetAsync with history and notes; Pages/Staff/Details.cshtml; _RequestFields and _HistoryList | Not in CI: Backend RequestServiceTests visibility cases. Planned in CI | at M4 | Changed (CR-010) | M. Malope with K. Marota | Pages/Staff/Details.cshtml.cs (view checked by policy first) | E2E-02 (walk-through) | Authorised staff see full details and history | Not run: needs a running RC (B2) | IN
FR-011 | Assign or accept responsibility for a request. | ST-2 | Must | AC-011.1; AC-011.2 | ASR-01 (primary) | FE accept -> entry -> Requests | requests schema: conditional update where unassigned, history in the same transaction | ADR-002 layered responsibility + conditional update (A2 Task 2 evidence); ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; CR-004; NFR-005; RSK-007; RSK-009; RSK-010; RSK-018 | Backend and UI branches | AssignmentService.AcceptAsync; RequestRepository.TryAssignAsync conditional update; Migrations/003_assignment.sql; Pages/Staff/Details.cshtml OnPostAcceptAsync | CI: AssignmentServiceTests (4 cases, run in the gate); ConcurrentAcceptTests skipped in CI until a test database is provided. Not in CI: Backend RealDatabaseTests | at M4 | Changed (CR-010), M2 trace requirement | K. Marota (build); M. Malope (trace and tests) | AssignmentService.AcceptAsync; RequestRepository.TryAssignAsync; POST /api/v1/requests/{id}/assignment (409 when owned); Details OnPostAcceptAsync | UT-03, IT-02, E2E-02 | Owner and timestamp recorded; a second accept gets 409 and the owner is unchanged; exactly one of 8 concurrent accepts succeeds | UT-03 AssignmentServiceTests: pending run. IT-02 ConcurrentAcceptTests: skipped in CI (no test DB, B3), counts as Blocked | IN
FR-012 | Update a request's status through controlled transitions. | ST-2 | Must | AC-012.1; AC-012.2 | ASR-01; ASR-03 | FE staff transition -> entry -> Requests | requests schema: guarded transitions, append-only history | ADR-002 explicit transition rules; ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; NFR-005; NFR-007; conflict C-1; RSK-009; RSK-010 | Backend and UI branches | StatusTransitionService.TransitionAsync; Core/Rules/StatusRules; Pages/Staff/Details.cshtml OnPostTransitionAsync | CI: StatusTransitionTests (4 allowed, 4 refused transitions). Not in CI: Backend StatusTransitionServiceTests and StatusRulesTests | at M4 | Changed (CR-010) | K. Marota | Domain/Requests/StatusTransition; StatusTransitionService.MoveAsync; not wired to a page or endpoint | UT-01, BB-04, E2E-02 | Only forward adjacent moves allowed; Received to Closed and backward moves refused with a message; each change recorded with actor and timestamp | UT-01 StatusTransitionTests: pending run. BB-04, E2E-02: not run (not wired) | IN*: gap, wire status endpoint and page actions
FR-013 | Record actions, comments or resolution information on a request. | ST-2 | Must | AC-013.1 | ASR-03 (primary) | FE staff note -> entry -> Requests | requests schema: append-only notes | ADR-002 append-only history | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; NFR-007; RSK-009; RSK-013 | Backend branch | Core/Services/NoteService; request_note table with an append only trigger. No screen yet | Not in CI: Backend NoteAndFeedbackTests (Only_the_owner_can_add_notes, An_empty_note_is_refused). Planned in CI | at M4 | Changed (CR-010) | K. Marota | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-014 | Resolve or close requests where authorised. | ST-2 | Must | AC-014.1; AC-014.2 | ASR-01; ASR-02 | FE resolve or close -> entry -> Requests (close permission from Access policy) | requests schema: resolution and feedback in the same transaction | ADR-002; ADR-005 close permission | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; ADR-005; NFR-006; RSK-011 | Backend and UI branches | TransitionAsync with the close permission; offered through NextStatuses on the staff page | Not in CI: Backend StatusTransitionServiceTests close cases. Planned in CI | at M4 | Changed (CR-010) | K. Marota with G. Enright | RequestAccess.MayWorkOn (owning, in-scope staff); no close flow yet | UT-04, IT-03, E2E-02 | Owning in-scope staff can close; requester, non-owner or out-of-scope staff refused and status unchanged | UT-04 RequestAccessTests: pending first run on frontend-milestone-3-development. IT-03: not run (no endpoint) | IN*: gap, comes with FR-012 wiring
FR-015 | View useful service-activity information (oversight overview). | ST-3 | Must | AC-015.1 | ASR-04 | FE oversight -> entry -> Reporting -> Requests API | No reporting copy; figures read through Requests (NFR-008) | ADR-004; ADR-006 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-001; NFR-008 | at M3 | at M3 | at M3 | at M4 | Baselined | M. Malope with K. Marota | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-016 | Identify open, overdue, resolved and closed requests. | ST-3 | Must | AC-016.1; AC-016.2 | ASR-04 | FE oversight filters -> entry -> Reporting -> Requests API | Needs target_response_at in the requests schema (CR-005) | ADR-004 | PostgreSQL 17.x; target response column not added (CR-005) | CR-005; ADR-002; RSK-018 | at M3 | Blocked pending CR-005 | at M3 | at M4 | Changed - blocked, CR-005 pending approval | M. Malope (CR); K. Marota (schema) | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-017 | View request information by category/status (or another justified dimension). | ST-3 | Must | AC-017.1 | ASR-04 | FE oversight grouping -> entry -> Reporting -> Requests API | No reporting copy; grouped through Requests | ADR-004; ADR-006 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006 | at M3 | at M3 | at M3 | at M4 | Baselined | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-018 | Access enough information to support accountability and service-performance analysis. | ST-3 | Should | AC-018.1; AC-018.2 | ASR-04 | FE reports -> entry -> Reporting -> Requests API | No reporting copy; export scope pending CR-006 | ADR-004 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-006; NFR-008; RSK-018 | at M3 | at M3 | at M3 | at M4 | Baselined - export scope pending CR-006 | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-019 | Manage user accounts. | ST-4 | Must | AC-019.1 | ASR-02 | FE admin users -> entry -> Access | access schema: users with active flag, no hard delete | ADR-005 identity and authorisation model | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; CR-003; RSK-012 | Backend branch | app_user table with is_active in Migrations/001_request.sql; Data/UserRepository. No admin screen | at M3 | at M4 | Changed (CR-010) | G. Enright | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-020 | Manage roles and permissions (RBAC). | ST-4 | Must | AC-020.1; AC-020.2 | ASR-02 (primary) | FE admin roles -> entry -> Access | access schema: roles, permissions, user roles | ADR-005 design decision 2: RBAC policy enforcement | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005 supersedes D-004; CR-003; NFR-006; RSK-012; RSK-016 | Backend branch | Migrations/005_rbac.sql (role, permission, role_permission, user_role) with the seeded matrix; Core/Rules/AuthorisationPolicy | CI: AssignmentServiceTests (The_policy_is_checked_before_anything_is_written). Not in CI: Backend permission cases | at M4 | Changed (CR-010) | G. Enright | Not built in either tree; roles seeded only | None (role-change rows dropped from UT-04) | n/a | n/a | OUT: Scope Freeze v1.0
FR-021 | Maintain the controlled category list. | ST-4 | Must | AC-021.1 | ASR-04 | FE admin categories -> entry -> ReferenceData | referencedata schema: editable categories, retire flag | ADR-006 reference-data endpoint | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-008; RSK-018 | at M3 | Category table supports retire; no admin screen | at M3 | at M4 | Baselined | G. Enright with M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-022 | Access an audit trail of key controlled actions. | ST-4 | Should | AC-022.1 | ASR-03 | FE admin audit -> entry -> Requests history, plus Access and ReferenceData change records | Append-only history in each owning schema | ADR-002 append-only; ADR-005 read permission | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; NFR-007; RSK-013 | Backend branch | request_status_history and request_note with block_history_changes triggers. Admin view not built | Not in CI: Backend RealDatabaseTests (History_rows_cannot_be_changed_or_deleted). Planned in CI | at M4 | Changed (CR-010) | G. Enright with K. Marota | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
FR-023 | Access high-level service-performance and accountability reporting. | ST-5 | Should | AC-023.1 | ASR-04 | FE summary reports -> entry -> Reporting -> Requests API | Same figures as FR-018 at summary scope | ADR-004 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-007; RSK-018 | at M3 | at M3 | at M3 | at M4 | Baselined - access model pending CR-007 | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
NFR-001 | Usability: a first-time requester can submit in ≤ 5 steps / 5 min. | ST-1 | Should | ≤ 5 steps and ≤ 5 min (usability test) | ASR-06 | FE guided submit form | None | ADR-004 one guided flow with per-field validation | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-004; RSK-016 | UI branch | One guided form on Pages/Requests/Submit.cshtml with a message against each field | Planned: moderated walkthrough with three first time users | at M4 | Changed (CR-010) | M. Malope | Not in app/ (needs the submit page) | Usability walkthrough (Role 1) | First-time requester submits in at most 5 steps and 5 minutes without training | Not run: blocked by B1 | IN*: blocked (B1)
NFR-002 | Feedback timeliness: a change is visible to the requester within 15 s. | ST-1 | Should | ≤ 15 s after a staff status change (measured) | ASR-06 | Requests -> entry -> FE polling | requests schema: feedback in the same transaction | ADR-002 pull-based refresh; no push infrastructure | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-001; ASR-06; RSK-018 | Backend branch | Feedback written in the same transaction as the status change (FeedbackService). No refresh on the requester screen yet | Planned: timed observation after a transition | at M4 | Changed - CR-001 pending approval | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
NFR-003 | Privacy: a requester can never view another requester's request. | ST-1 | Must | Access-control test; supports AC-004.2 | ASR-02 | Access policy, checked again in every service | requests schema: requester_id scoping on every read | ADR-005 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005 supersedes D-004; RSK-011 | Backend and UI branches | AuthorisationPolicy.CanSee; scoped queries in RequestRepository; requester pages load own rows only | Not in CI: Backend RequestServiceTests visibility cases. Planned: direct reference negative test | at M4 | Changed (CR-010) | G. Enright | RequestAccess.MayView requester rule; Staff/Details 404 outside policy | UT-04, BB-05 | A requester can never see another requester's request | UT-04 RequestAccessTests: pending first run on frontend-milestone-3-development. BB-05: not run (B1) | IN*: page blocked (B1)
NFR-004 | Performance: staff queue and oversight views load quickly under load. | ST-2, ST-3 | Should | ≤ 3 s for 1,000 requests (confirm target) | ASR-04 | Queue in Requests, oversight in Reporting | requests schema: indexes and paging | ADR-002; ADR-006 | PostgreSQL 17.x indexes; measured on the Render and Neon free plans (ADR-007) | CR-002; NFR-008; RSK-014; RSK-018 | Backend branch | Indexes ix_request_queue, ix_request_requester, ix_request_created in place. db/dev_seed.sql seeds a small set only | Planned: timed load at 1,000 seeded requests | at M4 | Changed - CR-002 pending approval | K. Marota with M. Malope | Staff queue query (indexed, capped at 50 rows) | PT-01 | 95th percentile at or below 3 s for 1,000 requests; zero errors | Not run: no staging RC (B2) | IN*: blocked (B2)
NFR-005 | Concurrency & integrity: no double-ownership or lost updates. | ST-2 | Must | No two owners; atomic transitions (supports FR-011/012) | ASR-01 | Requests only | requests schema: conditional updates, single-owner check | ADR-002 (A2 Task 2 research evidence) | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; RSK-007; RSK-010 | Backend branch | RequestRepository.TryAssignAsync and TryChangeStatusAsync guarded updates; version column; ck_request_owner_pair and ck_request_owner_vs_status | CI: AssignmentServiceTests; ConcurrentAcceptTests skipped in CI until a test database is provided. Not in CI: Backend RealDatabaseTests | at M4 | Changed (CR-010), M2 trace requirement | K. Marota | RequestRepository.TryAssignAsync and TryTransitionAsync guarded updates | UT-03, IT-02 | No double ownership; no lost status updates | UT-03: pending run. IT-02: skipped in CI (B3), counts as Blocked | IN: IT-02 blocked (B3)
NFR-006 | Security / RBAC: every action authorised by role. | ST-4 | Must | Unauthorised access denied (supports FR-008/014/020) | ASR-02 | Access policy, checked again in every service | access schema: role and permission rules | ADR-005 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; CR-003; RSK-011; RSK-012 | Backend and UI branches | AuthorisationPolicy.Require called by every service; capabilities on the pages come from the same permissions (UI/CapabilityFactory) | CI: AssignmentServiceTests policy check. Not in CI: Backend permission cases. Planned: role matrix test | at M4 | Changed (CR-010) | G. Enright | AuthorisationPolicy (fail closed) with RequestAccess; 403 on assignment endpoint | UT-04, IT-03 | Every action checked against role and scope; unauthorised actions denied and state unchanged | UT-04 RequestAccessTests: pending first run on frontend-milestone-3-development. IT-03: not run (no endpoint) | IN
NFR-007 | Auditability: key actions recorded and tamper-evident. | ST-4 | Must | Actor+timestamp, not silently altered (supports FR-013/022) | ASR-03 | Requests only, plus change records in Access and ReferenceData | Append-only history in each owning schema | ADR-002 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; RSK-009; RSK-013; RSK-015 | Backend branch | Append only history and notes enforced by the block_history_changes triggers, not only by the application | Not in CI: Backend RealDatabaseTests (History_rows_cannot_be_changed_or_deleted). Planned in CI | at M4 | Changed (CR-010) | K. Marota with G. Enright | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
NFR-008 | Reporting accuracy: reports reconcile with the underlying records. | ST-3, ST-5 | Should | No discrepancy between report and data | ASR-04 | Reporting reads through Requests | No duplicated store | ADR-001 no separate reporting database | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-001 | at M3 | Reporting reads the same tables; no reporting screen yet | at M3 | at M4 | Baselined | K. Marota | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
NFR-009 | Cost sustainability: run within free/low-cost tiers where practical. | ST-5 | Should | Runs within free/low-cost tiers; cost documented | ASR-05 | Four services, entry point and FE on free tiers | One shared PostgreSQL instance, schema per service | ADR-007 deployment direction | Render free tier and Neon free plan (ADR-007) | ADR-007; RSK-006; RSK-014; RSK-015; RSK-019 | at M3 | Not deployed yet; plan limits recorded in ADR-007 | Planned: cost sheet against the plan limits | at M4 | Baselined | G. Enright | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)
NFR-010 | Growth readiness: able to expand in future without a redesign (added through CR-011). | ST-5 | Must | Scale-out, data ownership and extension checks all pass (NFR-010) | ASR-07 | All services | Schema per service, no cross-schema access | ADR-004 revision 2: one web frontend service with no in-memory session state | Pending revised ADR-001 (CR-010) | CR-010; CR-011; ADR-001; ADR-004 | at M3 | Planned | Planned: FR-011 concurrent-accept check against two copies of the owning service | at M4 | Candidate (CR-011) | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0)