## RTM
CivicConnect Requirements Traceability Matrix (RTM) - v4.0 FINAL, release v1.0.0, live at https://sen381-project-group-i-2026.onrender.com/. Evidence: 288/288 automated tests pass (18 Oct 2026, PostgreSQL 17); simulated production 13/13 (Test/Evidence/Final_Simulated_Production.md); hosted checks (Test/Evidence/Hosted_Deployment_Check.md). Column O gives the M4 release evidence; columns W and X give each acceptance criterion's final status and each requirement's final outcome. Scope completion: 45 of 46 = 97.8% (PED v4.0).
Req ID | Requirement | Source (Stakeholder) | Priority | Acceptance Criteria | ASR / Quality Driver (new at M2) | Design / Architecture (M2) | Data / Persistence (new at M2) | Design / Interface Decision (new at M2) | Technology Decision (new at M2) | ADR / Change / Risk (new at M2) | Issue / PR (â†’ M3) | Implementation (â†’ M3) | Test / Verification (â†’ M3) | Acceptance / Release Evidence (â†’ M4) | Status | Owner | RC Implementation (app/, M3) | Test Case(s) (Test Plan v1) | Expected Result (M3) | Execution Evidence (M3) | Defect / M3 Status | Final AC Status (M4, v1.0.0) | Final Outcome (M4)
FR-001 | Submit a new service request with the information needed to action it. | ST-1 | Must | AC-001.1; AC-001.2 | ASR-06 | FE submit page -> entry -> Requests | requests schema: request row, ref ID, status Received; category ID checked through the ReferenceData API, no cross-schema FK | ADR-004 view composition; ADR-006 per-field validation errors | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-001; ADR-004; ADR-006; RSK-008; RSK-019 | Backend and UI branches | Core/Services/RequestService.SubmitAsync; Data/Migrations/001_request.sql; Pages/Requests/Submit.cshtml | Not in CI: Backend RequestServiceTests (Overlong_title_is_refused, Staff_cannot_submit_requests_without_the_permission). Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope with K. Marota | SubmissionService; Pages/Requests/Submit; POST /api/v1/requests; Location and reference sequence (migration AddStaffScopesLocationAndReferences) | UT-05, BB-01, BB-02, IT-01, E2E-01 | Valid request saved with a unique reference ID and status Received; a missing field blocks the save and is flagged; over-limit input rejected without a server error | UT-05, BB-01, BB-02, IT-01, E2E-01 pass (automated). AC-001.1, AC-001.2, BB-02 pass (acceptance) | IN | AC-001.1 Met; AC-001.2 Met | IMPLEMENTED
FR-002 | Categorise the request from a controlled category list (not free text). | ST-1, ST-3 | Must | AC-002.1; AC-002.2 | ASR-04; ASR-06 | FE category select -> entry -> ReferenceData | referencedata schema: category table, retired kept | ADR-004; ADR-006 reference-data endpoint | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006; CR-008; RSK-018 | Backend and UI branches | Core/Services/CategoryService; Data/Migrations/002_category.sql; category select on Pages/Requests/Submit.cshtml | Not in CI: covered indirectly by Backend RequestServiceTests. Planned: category test in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope | IRequestQueries.ListActiveCategoriesAsync feeds the Submit select from reference data; SubmissionService rejects unknown or retired categories | UT-02 | Only listed categories accepted; unknown, empty or null category rejected and flagged | UT-02 pass (automated). AC-002.1, AC-002.2 pass (acceptance) | IN | AC-002.1 Met; AC-002.2 Met | IMPLEMENTED
FR-003 | View the current status of a submitted request. | ST-1 | Must | AC-003.1; AC-003.2 | ASR-06; ASR-01 | FE status view -> entry -> Requests | requests schema: constrained status, read-only to requesters | ADR-004 read-only status display (resolves C-1) | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-004; conflict C-1; RSK-016 | UI branch | Core/Services/RequestService.GetAsync; Pages/Requests/Details.cshtml; TagHelpers/StatusBadgeTagHelper | Not in CI: Backend StatusRulesTests (Display_text_is_plain_language). Planned: page test for AC-003.2 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope | Pages/Requests/Details (read only, policy View first); Shared/_RequestFields; StatusBadgeTagHelper | E2E-01 | Owned request shows its status in plain language; no control to change it | E2E-01 pass (automated). AC-003.1, AC-003.2 pass (acceptance) | IN | AC-003.1 Met; AC-003.2 Met | IMPLEMENTED
FR-004 | View a history/list of own previously submitted requests. | ST-1 | Must | AC-004.1; AC-004.2 | ASR-02; ASR-06 | FE history -> entry -> Requests (scope from Access policy) | requests schema: scoped by requester_id, indexed | ADR-005 server-side ownership scoping; ADR-004 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; NFR-003; RSK-011 | Backend and UI branches | RequestService.ListOwnAsync; Pages/Requests/Index.cshtml; index ix_request_requester | Not in CI: Backend RequestServiceTests scope cases. Planned: negative access test | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope with G. Enright | Pages/Requests/Index; RequestQueries.ListForRequesterAsync scoped to the requester; RequestAccess.MayView | UT-04, BB-05, E2E-01 | History lists only the requester's own requests; another requester's request returns not found with no data | BB-05, E2E-01 pass (automated). AC-004.1, BB-05 pass (acceptance) | IN | AC-004.1 Met; AC-004.2 Met | IMPLEMENTED
FR-005 | Search/filter own request history. | ST-1 | Should | AC-005.1 | ASR-04 | FE filter -> entry -> Requests | requests schema: (requester_id, status) index, paging | ADR-004; ADR-006 query parameters | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006 | UI branch | Status filter on Pages/Requests/Index.cshtml; ListOwnAsync paging | Planned: filter and empty state page test | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Changed (CR-010) | M. Malope | Pages/Requests/Index status filter; RequestQueries.ListForRequesterAsync filters on the requester and the status inside the query | ManagementScreensTests (FR-005) | Only the requester's own requests with the chosen status are listed; a message when none match | ManagementScreensTests pass (automated, 16 Oct 2026) | IN (CR-016) | AC-005.1 Met | IMPLEMENTED (CR-016)
FR-006 | Attach supporting information to a request (e.g. a photo). | ST-1, ST-2 | Could | AC-006.1 | ASR-05 (cost/complexity) | Not allocated (deferred) | None | Deferred - no design decision taken | Deferred, storage not selected | PED Scope (Deferred); CR required to re-scope; RSK-003; RSK-018 | PR #34 (frontend-milestone-3-development, CR-016) | at M3 | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Candidate - may defer | K. Marota on re-scope | AttachmentService; RequestAttachment (JPG, PNG or PDF checked by file signature, 5 MB, 5 per request), stored in PostgreSQL (request_attachments); upload on Requests/Details and Staff/Details; GET /api/v1/requests/{id}/attachments/{attachmentId} | RequestAttachmentTests, AttachmentServiceTests, AttachmentTests, RequestAccessTests (FR-006) | An allowed file is stored and linked to the request; a disallowed type or size is refused with a message; only people who may view the request can download it | RequestAttachmentTests, AttachmentServiceTests, AttachmentTests pass (automated, 16 Oct 2026), including a renamed non-image file and a file over 5 MB refused | IN (CR-016) | AC-006.1 Met | IMPLEMENTED (deferred Could at M1; brought in by CR-016)
FR-007 | Receive feedback when a request is accepted, rejected, updated or completed. | ST-1 | Must | AC-007.1; AC-007.2 | ASR-06; ASR-05 | Requests writes feedback with the status change -> entry -> FE | requests schema: feedback item in the same transaction as the status change | ADR-002 same-transaction write; in-app pull only, no push | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; conflict C-4; CR-001; RSK-009; RSK-018 | Backend branch | Core/Services/FeedbackService; Data/Migrations/004_feedback.sql; FeedbackController. No requester screen yet | Not in CI: Backend NoteAndFeedbackTests (Nobody_can_mark_someone_elses_feedback_as_read). Planned: timing check | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope with K. Marota | Assignment and status changes write RequesterFeedback; Pages/Requests/Details lists the updates; a rejection sends its reason to the requester (CR-009); status and updates refresh by polling every 5 s (NFR-002) | E2E-02, StatusTransitionServiceTests (AC-007.2), UpdatesPollingTests | A timestamped update for each change, shown to the requester; a rejected request tells the requester why | E2E-02, StatusTransitionServiceTests, UpdatesPollingTests pass (automated, 16 Oct 2026). AC-007.1 pass (acceptance) | IN (AC-007.2 built by CR-009) | AC-007.1 Met; AC-007.2 Met (Rejected status, CR-009) | IMPLEMENTED
FR-008 | View the service requests relevant to authorised staff (staff queue). | ST-2 | Must | AC-008.1; AC-008.2 | ASR-02; ASR-04 | FE staff queue -> entry -> Requests | requests schema: queue indexes (status, category, assigned_to) | ADR-005 policy check per query; ADR-004 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; NFR-006; RSK-011 | Backend and UI branches | RequestService.QueueAsync; Pages/Staff/Queue.cshtml; index ix_request_queue | Not in CI: Backend RequestServiceTests (The_queue_is_closed_to_requesters). Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope with G. Enright | IQueueRepository and Staff/Queue scoped by category; scope check in AuthorisationPolicy; Staff/Details 404 outside scope | UT-04, BB-03, QueueTests | Queue lists only requests in the staff member's categories; opening an out-of-scope request by ID returns 404 with no request data | UT-04, QueueTests pass (automated). BB-03a to BB-03e pass (acceptance) | IN | AC-008.1 Met; AC-008.2 Met | IMPLEMENTED
FR-009 | Search, filter or sort requests using useful criteria. | ST-2 | Must | AC-009.1; AC-009.2 | ASR-04 | FE queue filter and sort -> entry -> Requests | requests schema: indexes, sort whitelist, paging | ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006; NFR-004 | Backend and UI branches | Sort whitelist in RequestService.QueueAsync and RequestRepository; status filter on the queue page | Planned: sort and filter tests | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope | IQueueRepository.SearchAsync (filter, search, sort, paging); GET /api/v1/queue; Staff/Queue filter bar | QueueTests, ApiTests, StaffScreensTests | Only matching requests in the staff member's scope, in the chosen order; a message when none match | QueueTests, ApiTests, StaffScreensTests pass (automated). Search and filter pass (acceptance) | IN | AC-009.1 Met; AC-009.2 Met | IMPLEMENTED
FR-010 | View the full details of a request. | ST-2 | Must | AC-010.1 | ASR-02; ASR-03 | FE staff detail -> entry -> Requests | requests schema: request with history and notes | ADR-005; ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; RSK-011 | Backend and UI branches | RequestService.GetAsync with history and notes; Pages/Staff/Details.cshtml; _RequestFields and _HistoryList | Not in CI: Backend RequestServiceTests visibility cases. Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | M. Malope with K. Marota | Pages/Staff/Details with Shared/_RequestFields (requester, category, location), policy checked first | AC-010.1 check, E2E-02 (walk-through) | Authorised staff see full details and history | AC-010.1 pass (acceptance); DEF-001 fixed | IN | AC-010.1 Met (DEF-001 fixed) | IMPLEMENTED
FR-011 | Assign or accept responsibility for a request. | ST-2 | Must | AC-011.1; AC-011.2 | ASR-01 (primary) | FE accept -> entry -> Requests | requests schema: conditional update where unassigned, history in the same transaction | ADR-002 layered responsibility + conditional update (A2 Task 2 evidence); ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; CR-004; NFR-005; RSK-007; RSK-009; RSK-010; RSK-018 | Backend and UI branches | AssignmentService.AcceptAsync; RequestRepository.TryAssignAsync conditional update; Migrations/003_assignment.sql; Pages/Staff/Details.cshtml OnPostAcceptAsync | CI: AssignmentServiceTests (4 cases, run in the gate); ConcurrentAcceptTests skipped in CI until a test database is provided. Not in CI: Backend RealDatabaseTests | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010), M2 trace requirement | K. Marota (build); M. Malope (trace and tests) | AssignmentService.AcceptAsync; RequestRepository.TryAssignAsync; POST /api/v1/requests/{id}/assignment (409 when owned); Details OnPostAcceptAsync; Staff/Queue accept from the row (same AssignmentService) | UT-03, IT-02, E2E-02, StaffScreensTests (accept from the queue row) | Owner and timestamp recorded; a second accept gets 409 and the owner is unchanged; exactly one of 8 concurrent accepts succeeds | UT-03, IT-02, eight-staff API race and StaffScreensTests (accept from the queue row, a second accept refused) pass (automated). AC-011.1, AC-011.2 pass (acceptance) | IN | AC-011.1 Met; AC-011.2 Met | IMPLEMENTED
FR-012 | Update a request's status through controlled transitions. | ST-2 | Must | AC-012.1; AC-012.2 | ASR-01; ASR-03 | FE staff transition -> entry -> Requests | requests schema: guarded transitions, append-only history | ADR-002 explicit transition rules; ADR-006 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; NFR-005; NFR-007; conflict C-1; RSK-009; RSK-010 | Backend and UI branches | StatusTransitionService.TransitionAsync; Core/Rules/StatusRules; Pages/Staff/Details.cshtml OnPostTransitionAsync | CI: StatusTransitionTests (4 allowed, 4 refused transitions). Not in CI: Backend StatusTransitionServiceTests and StatusRulesTests | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | K. Marota | StatusTransitionService.MoveAsync; Staff/Details status form; POST /api/v1/requests/{id}/status (POST, not PATCH: CR-015); RejectAsync: Received to Rejected only, with a reason (CR-009); the database check constraints allow Rejected with no owner | UT-01, BB-04, E2E-02, StatusTransitionTests (Rejected) | Only forward adjacent moves allowed; Received to Closed and backward moves refused with a message; Rejected only from Received; each change recorded with actor and timestamp | UT-01, StatusTransitionTests (including Rejected), StatusTransitionServiceTests, LifecycleTests, E2E-02 pass (automated). AC-012.1, AC-012.2 pass (acceptance) | IN | AC-012.1 Met; AC-012.2 Met | IMPLEMENTED
FR-013 | Record actions, comments or resolution information on a request. | ST-2 | Must | AC-013.1 | ASR-03 (primary) | FE staff note -> entry -> Requests | requests schema: append-only notes | ADR-002 append-only history | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; NFR-007; RSK-009; RSK-013 | Backend branch | Core/Services/NoteService; request_note table with an append only trigger. No screen yet | Not in CI: Backend NoteAndFeedbackTests (Only_the_owner_can_add_notes, An_empty_note_is_refused). Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | K. Marota | NoteService; POST /api/v1/requests/{id}/notes; Staff/Details add-note form | NoteServiceTests, ApiTests, StaffScreensTests | A note is saved to the history with author and time and is never edited | NoteServiceTests, ApiTests, StaffScreensTests pass (automated). Add a note pass (acceptance) | IN | AC-013.1 Met | IMPLEMENTED
FR-014 | Resolve or close requests where authorised. | ST-2 | Must | AC-014.1; AC-014.2 | ASR-01; ASR-02 | FE resolve or close -> entry -> Requests (close permission from Access policy) | requests schema: resolution and feedback in the same transaction | ADR-002; ADR-005 close permission | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; ADR-005; NFR-006; RSK-011 | Backend and UI branches | TransitionAsync with the close permission; offered through NextStatuses on the staff page | Not in CI: Backend StatusTransitionServiceTests close cases. Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); M3 acceptance checks pass (Test/Evidence/M3_Acceptance_Checks.md) | Changed (CR-010) | K. Marota with G. Enright | Close checked as its own action: the owner in scope or an administrator (CR-012); resolving needs a note | UT-04, IT-03, E2E-02 | Owning in-scope staff can close; requester, non-owner or out-of-scope staff refused and status unchanged | IT-03, E2E-02, AuthorisationTests pass (automated). AC-014.1, AC-014.2, administrator close pass (acceptance) | IN: AC-014.2 reworded by CR-012 (proposed) | AC-014.1 Met; AC-014.2 Met as reworded by CR-012 | IMPLEMENTED (AC-014.2 changed through CR-012)
FR-015 | View useful service-activity information (oversight overview). | ST-3 | Must | AC-015.1 | ASR-04 | FE oversight -> entry -> Reporting -> Requests API | No reporting copy; figures read through Requests (NFR-008) | ADR-004; ADR-006 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-001; NFR-008 | PR #34 (frontend-milestone-3-development, CR-016) | at M3 | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Baselined | M. Malope with K. Marota | IOversightQueries.SummaryAsync; Pages/Oversight for managers and administrators: headline figures, counts by status and category, most recent requests | ManagementScreensTests (FR-015), ReportingTests, RequestAccessTests | Managers and administrators see activity figures that match the request records; other roles are refused | ManagementScreensTests, ReportingTests pass (automated, 16 Oct 2026) | IN (CR-016) | AC-015.1 Met | IMPLEMENTED (CR-016)
FR-016 | Identify open, overdue, resolved and closed requests. | ST-3 | Must | AC-016.1; AC-016.2 | ASR-04 | FE oversight filters -> entry -> Reporting -> Requests API | Needs target_response_at in the requests schema (CR-005) | ADR-004 | PostgreSQL 17.x; target response column not added (CR-005) | CR-005; ADR-002; RSK-018 | PR #34 (frontend-milestone-3-development, CR-016) | Blocked pending CR-005 | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Changed - blocked, CR-005 pending approval | M. Malope (CR); K. Marota (schema) | Category.TargetResponseHours (default 72, set on Admin/Categories); Request.TargetResponseAtUtc fixed at submission (CR-005, migration AddRemainingRequirements); ResponseTarget.IsOverdue; Oversight Open and Overdue filter; overdue rows tagged on Oversight and Staff/Queue | ResponseTargetTests, CategoryServiceTests, SubmissionServiceTests (FR-016), ReportingTests (AC-016.1, AC-016.2, CR-005), StaffScreensTests (AC-016.2) | Open, resolved, closed and rejected requests are each identifiable; an open request past its target is flagged as overdue | ResponseTargetTests, CategoryServiceTests, SubmissionServiceTests, ReportingTests, StaffScreensTests pass (automated, 16 Oct 2026) | IN (CR-016; CR-005 approved) | AC-016.1 Met; AC-016.2 Met | IMPLEMENTED (CR-016; target field CR-005)
FR-017 | View request information by category/status (or another justified dimension). | ST-3 | Must | AC-017.1 | ASR-04 | FE oversight grouping -> entry -> Reporting -> Requests API | No reporting copy; grouped through Requests | ADR-004; ADR-006 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-006 | PR #34 (frontend-milestone-3-development, CR-016) | at M3 | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Baselined | M. Malope | Oversight status, category and state filters; every figure and the performance table follow the same filter (OversightQueries) | ManagementScreensTests, ReportingTests | Counts by status and by category update together when a status, category or state is chosen | ManagementScreensTests (counts follow the filters), ReportingTests pass (automated, 16 Oct 2026) | IN (CR-016) | AC-017.1 Met | IMPLEMENTED (CR-016)
FR-018 | Access enough information to support accountability and service-performance analysis. | ST-3 | Should | AC-018.1; AC-018.2 | ASR-04 | FE reports -> entry -> Reporting -> Requests API | No reporting copy; export scope pending CR-006 | ADR-004 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-006; NFR-008; RSK-018 | PR #34 (frontend-milestone-3-development, CR-016) | at M3 | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Baselined - export scope pending CR-006 | M. Malope | Oversight service performance table by category (volumes, open, overdue, resolved, resolved within target, average hours to resolve); CSV export of the table and of the matching requests (CR-006) | ReportingTests (AC-018.2, NFR-008) | Performance figures in enough detail for accountability; the exported data matches what is displayed; only managers and administrators can export | ReportingTests pass (automated, 16 Oct 2026): the exported table equals the displayed table row for row, and staff get 403 | IN (CR-016; CR-006 approved) | AC-018.1 Met; AC-018.2 Met | IMPLEMENTED (CR-016; export CR-006)
FR-019 | Manage user accounts. | ST-4 | Must | AC-019.1 | ASR-02 | FE admin users -> entry -> Access | access schema: users with active flag, no hard delete | ADR-005 identity and authorisation model | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; CR-003; RSK-012 | Backend branch | app_user table with is_active in Migrations/001_request.sql; Data/UserRepository. No admin screen | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); simulated production 13/13 with real sign-in | Changed (CR-010) | G. Enright | UserService (create, deactivate, reactivate; accounts never deleted); Admin/Users; AppUser.IsActive; AuthorisationPolicy and the development sign-in refuse deactivated users | AppUserTests, UserServiceTests (FR-019), UserAdminTests (AC-019.1), LandingPageTests (AC-019.1), RoleMatrixTests | An administrator creates or deactivates a user; a deactivated user can no longer sign in or act, from their next request | AppUserTests, UserServiceTests, UserAdminTests, LandingPageTests, RoleMatrixTests pass (automated, 16 Oct 2026); with real sign-in, SignInTests and AppUserSignInTests pass (18 Oct 2026, 287/287), including a deactivated user losing the session at once | IN (CR-016, CR-003) | AC-019.1 Met (real sign-in: a deactivated user loses the session at once) | IMPLEMENTED (CR-016; sign-in CR-003, ADR-008)
FR-020 | Manage roles and permissions (RBAC). | ST-4 | Must | AC-020.1; AC-020.2 | ASR-02 (primary) | FE admin roles -> entry -> Access | access schema: roles, permissions, user roles | ADR-005 design decision 2: RBAC policy enforcement | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005 supersedes D-004; CR-003; NFR-006; RSK-012; RSK-016 | Backend branch | Migrations/005_rbac.sql (role, permission, role_permission, user_role) with the seeded matrix; Core/Rules/AuthorisationPolicy | CI: AssignmentServiceTests (The_policy_is_checked_before_anything_is_written). Not in CI: Backend permission cases | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); simulated production 13/13 with real sign-in | Changed (CR-010) | G. Enright | UserService.ChangeRoleAsync and SetScopesAsync; Admin/Users; roles stored as data, permissions per role in AuthorisationPolicy (ADR-005); an administrator cannot change their own role | UserServiceTests (FR-020, AC-020.2), UserAdminTests (AC-020.1, AC-020.2), RoleMatrixTests (TC-N006) | After a role change the user's permitted actions match the new role; a non-administrator cannot change roles | UserServiceTests, UserAdminTests, RoleMatrixTests pass (automated); SignInTests confirm only administrators manage accounts with real sign-in (18 Oct 2026) | IN (CR-016, CR-003) | AC-020.1 Met; AC-020.2 Met | IMPLEMENTED (CR-016)
FR-021 | Maintain the controlled category list. | ST-4 | Must | AC-021.1 | ASR-04 | FE admin categories -> entry -> ReferenceData | referencedata schema: editable categories, retire flag | ADR-006 reference-data endpoint | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-008; RSK-018 | PR #34 (frontend-milestone-3-development, CR-016) | Category table supports retire; no admin screen | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Baselined | G. Enright with M. Malope | CategoryService (add, rename, retire, restore, set target); Admin/Categories; the submit form reads the live list | CategoryServiceTests (FR-021), ManagementScreensTests (FR-021) | An administrator changes the category list with no code change and the submit form follows; duplicate names refused | CategoryServiceTests, ManagementScreensTests pass (automated, 16 Oct 2026) | IN (CR-016) | AC-021.1 Met | IMPLEMENTED (CR-016)
FR-022 | Access an audit trail of key controlled actions. | ST-4 | Should | AC-022.1 | ASR-03 | FE admin audit -> entry -> Requests history, plus Access and ReferenceData change records | Append-only history in each owning schema | ADR-002 append-only; ADR-005 read permission | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; NFR-007; RSK-013 | Backend branch | request_status_history and request_note with block_history_changes triggers. Admin view not built | Not in CI: Backend RealDatabaseTests (History_rows_cannot_be_changed_or_deleted). Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Changed (CR-010) | G. Enright with K. Marota | Admin/Audit combines request history with the insert-only audit_entries table (category, user and role changes), filtered by kind | ManagementScreensTests (FR-022), UserAdminTests (FR-022), AttachmentTests | Key controlled actions are listed with actor and time, for administrators only | ManagementScreensTests, UserAdminTests, AttachmentTests pass (automated, 16 Oct 2026) | IN (CR-016) | AC-022.1 Met | IMPLEMENTED (CR-016)
FR-023 | Access high-level service-performance and accountability reporting. | ST-5 | Should | AC-023.1 | ASR-04 | FE summary reports -> entry -> Reporting -> Requests API | Same figures as FR-018 at summary scope | ADR-004 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-007; RSK-018 | PR #34 (frontend-milestone-3-development, CR-016) | at M3 | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Baselined - access model pending CR-007 | M. Malope | Sponsor role (CR-007); Pages/Reports/Summary reuses the oversight figures at summary level, with no individual requests | ReportingTests (AC-023.1), RequestAccessTests (FR-023) | Sponsors, managers and administrators see summary figures that match the records; sponsors see no request details | ReportingTests, RequestAccessTests pass (automated, 16 Oct 2026) | IN (CR-016; CR-007 approved) | AC-023.1 Met | IMPLEMENTED (CR-016; sponsor view CR-007)
NFR-001 | Usability: a first-time requester can submit in ≤ 5 steps / 5 min. | ST-1 | Should | ≤ 5 steps and ≤ 5 min (usability test) | ASR-06 | FE guided submit form | None | ADR-004 one guided flow with per-field validation | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-004; RSK-016 | UI branch | One guided form on Pages/Requests/Submit.cshtml with a message against each field | Planned: moderated walkthrough with three first time users | v1.0.0: timed first-user walkthrough met the target (PED v4.0, M1 Scope to Final Delivery) | Changed (CR-010) | M. Malope | Pages/Requests/Submit: title, description, location, category, submit (five steps) | Usability walkthrough (Role 1) | First-time requester submits in at most 5 steps and 5 minutes without training | Timed first-user walkthrough run: met the five-step, five-minute target (PED v4.0, M1 Scope to Final Delivery) | IN: walkthrough done (Role 1) | Met: a first-time requester submitted without training within 5 steps and 5 minutes | IMPLEMENTED
NFR-002 | Feedback timeliness: a change is visible to the requester within 15 s. | ST-1 | Should | ≤ 15 s after a staff status change (measured) | ASR-06 | Requests -> entry -> FE polling | requests schema: feedback in the same transaction | ADR-002 pull-based refresh; no push infrastructure | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | CR-001; ASR-06; RSK-018 | Backend branch | Feedback written in the same transaction as the status change (FeedbackService). No refresh on the requester screen yet | Planned: timed observation after a transition | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Changed - CR-001 pending approval | M. Malope | status-poll.js refreshes the requester's status and updates every 5 s through the Requests/Details Updates handler (ADR-003 polling) | UpdatesPollingTests (NFR-002) | A staff status change is visible on the requester's page within 15 s | UpdatesPollingTests pass (automated, 16 Oct 2026): the change appears in the next poll, well inside 15 s. Measured in process, not over a network | IN (CR-016) | Met (5 s polling, UpdatesPollingTests) | IMPLEMENTED (CR-016)
NFR-003 | Privacy: a requester can never view another requester's request. | ST-1 | Must | Access-control test; supports AC-004.2 | ASR-02 | Access policy, checked again in every service | requests schema: requester_id scoping on every read | ADR-005 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005 supersedes D-004; RSK-011 | Backend and UI branches | AuthorisationPolicy.CanSee; scoped queries in RequestRepository; requester pages load own rows only | Not in CI: Backend RequestServiceTests visibility cases. Planned: direct reference negative test | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Changed (CR-010) | G. Enright | RequestAccess.MayView; requester queries scoped to the requester; Requests/Details returns 404 outside the policy | UT-04, BB-05, AttachmentTests, UpdatesPollingTests (NFR-003) | A requester can never see another requester's request | UT-04, BB-05, AttachmentTests, UpdatesPollingTests pass (automated). BB-05 pass (acceptance) | IN | Met | IMPLEMENTED
NFR-004 | Performance: staff queue and oversight views load quickly under load. | ST-2, ST-3 | Should | ≤ 3 s for 1,000 requests (confirm target) | ASR-04 | Queue in Requests, oversight in Reporting | requests schema: indexes and paging | ADR-002; ADR-006 | PostgreSQL 17.x indexes; measured on the Render and Neon free plans (ADR-007) | CR-002; NFR-008; RSK-014; RSK-018 | Backend branch | Indexes ix_request_queue, ix_request_requester, ix_request_created in place. db/dev_seed.sql seeds a small set only | Planned: timed load at 1,000 seeded requests | v1.0.0: PT-01 p95 0.064 s (Test/Evidence/PT-01_Results.md); hosted pages p95 under 1 s (Test/Evidence/Hosted_Deployment_Check.md) | Changed - CR-002 pending approval | K. Marota with M. Malope | IQueueRepository query, indexed and paged at 20 rows | PT-01, QueueTests | 95th percentile at or below 3 s for 1,000 requests; zero errors | PT-01 pass: p95 0.064 s with 5 users, 0 errors (Test/Evidence/PT-01_Results.md). QueueTests 1,000-request check pass | IN: measured locally; staging pending (B2) | Met: PT-01 p95 0.064 s locally against 3 s at 1,000 requests; on the hosted site the public pages answer with a p95 under 1 s (the queue itself was not timed there) | IMPLEMENTED
NFR-005 | Concurrency & integrity: no double-ownership or lost updates. | ST-2 | Must | No two owners; atomic transitions (supports FR-011/012) | ASR-01 | Requests only | requests schema: conditional updates, single-owner check | ADR-002 (A2 Task 2 research evidence) | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; RSK-007; RSK-010 | Backend branch | RequestRepository.TryAssignAsync and TryChangeStatusAsync guarded updates; version column; ck_request_owner_pair and ck_request_owner_vs_status | CI: AssignmentServiceTests; ConcurrentAcceptTests skipped in CI until a test database is provided. Not in CI: Backend RealDatabaseTests | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Changed (CR-010), M2 trace requirement | K. Marota | RequestRepository.TryAssignAsync and TryTransitionAsync guarded updates | UT-03, IT-02 | No double ownership; no lost status updates | UT-03, IT-02, eight-staff API race pass (automated) | IN | Met | IMPLEMENTED
NFR-006 | Security / RBAC: every action authorised by role. | ST-4 | Must | Unauthorised access denied (supports FR-008/014/020) | ASR-02 | Access policy, checked again in every service | access schema: role and permission rules | ADR-005 | Razor Pages; ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-005; CR-003; RSK-011; RSK-012 | Backend and UI branches | AuthorisationPolicy.Require called by every service; capabilities on the pages come from the same permissions (UI/CapabilityFactory) | CI: AssignmentServiceTests policy check. Not in CI: Backend permission cases. Planned: role matrix test | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026); simulated production 13/13 with real sign-in; the live site refuses anonymous access (Test/Evidence/Hosted_Deployment_Check.md) | Changed (CR-010) | G. Enright | AuthorisationPolicy (fail closed) with RequestAccess; 403 on assignment endpoint | UT-04, IT-03, RoleMatrixTests (TC-N006) | Every action checked against role and scope; unauthorised actions denied and state unchanged | UT-04, IT-03, AuthorisationTests, RoleMatrixTests pass (automated); SignInTests (pages 302 and API 401 until sign-in) pass; simulated production 13/13 (18 Oct 2026) | IN (real sign-in, CR-003) | Met (policy plus real sign-in outside Development) | IMPLEMENTED (CR-003)
NFR-007 | Auditability: key actions recorded and tamper-evident. | ST-4 | Must | Actor+timestamp, not silently altered (supports FR-013/022) | ASR-03 | Requests only, plus change records in Access and ReferenceData | Append-only history in each owning schema | ADR-002 | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-002; RSK-009; RSK-013; RSK-015 | Backend branch | Append only history and notes enforced by the block_history_changes triggers, not only by the application | Not in CI: Backend RealDatabaseTests (History_rows_cannot_be_changed_or_deleted). Planned in CI | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026), including the DEF-002 test (HistoryInsertOnlyTests) | Changed (CR-010) | K. Marota with G. Enright | request_history and audit_entries are insert-only, enforced by database triggers; every controlled action records its actor and time | HistoryInsertOnlyTests | Key actions are recorded with actor and timestamp and cannot be silently altered or deleted | HistoryInsertOnlyTests pass (automated, 18 Oct 2026): an UPDATE or DELETE on request_history or audit_entries is refused by the insert-only trigger (DEF-002 closed) | IN (CR-016) | Met: request_history and audit_entries are insert-only and both triggers are tested directly (DEF-002 closed) | IMPLEMENTED (CR-016)
NFR-008 | Reporting accuracy: reports reconcile with the underlying records. | ST-3, ST-5 | Should | No discrepancy between report and data | ASR-04 | Reporting reads through Requests | No duplicated store | ADR-001 no separate reporting database | ASP.NET Core on .NET 10 (C# 13); Npgsql with SQL migrations; PostgreSQL 17.x (ADR-003) | ADR-001 | PR #34 (frontend-milestone-3-development, CR-016) | Reporting reads the same tables; no reporting screen yet | at M3 | v1.0.0: the column U tests pass (288/288, CI green on main, 18/10/2026) | Baselined | K. Marota | Every oversight, summary and export figure is counted from the request rows with one filter (OversightQueries) | ReportingTests (NFR-008, AC-018.2) | Report figures, the list and the exports reconcile with the request records | ReportingTests pass (automated, 16 Oct 2026): totals equal the database count and the category rows add up to the total row | IN (CR-016) | Met | IMPLEMENTED (CR-016)
NFR-009 | Cost sustainability: run within free/low-cost tiers where practical. | ST-5 | Should | Runs within free/low-cost tiers; cost documented | ASR-05 | Four services, entry point and FE on free tiers | One shared PostgreSQL instance, schema per service | ADR-007 deployment direction | Render free tier and Neon free plan (ADR-007) | ADR-007; RSK-006; RSK-014; RSK-015; RSK-019 | PR #39 (Host setup: Dockerfile and Render deployment) | Deployed: Dockerfile on a Render Free web service, database on Neon Free (PR #39); plan limits in ADR-007 | Planned: cost sheet against the plan limits | v1.0.0: live on Render Free and Neon Free at $0 per month (Test/Evidence/Hosted_Deployment_Check.md; ADR-007) | Baselined | G. Enright | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0) | Met: runs live on Render Free and Neon Free at $0 per month (both plans confirmed Free); cost and limits recorded in ADR-007 | IMPLEMENTED (TD-04 repaid)
NFR-010 | Growth readiness: able to expand in future without a redesign (added through CR-011). | ST-5 | Must | Scale-out, data ownership and extension checks all pass (NFR-010) | ASR-07 | All services | Schema per service, no cross-schema access | ADR-004 revision 2: one web frontend service with no in-memory session state | Pending revised ADR-001 (CR-010) | CR-010; CR-011; ADR-001; ADR-004 | None: the service split was not built (CR-014) | Planned | Planned: FR-011 concurrent-accept check against two copies of the owning service | None: not implemented; accepted as technical debt (CR-014, TD-01) | Candidate (CR-011) | M. Malope | n/a | None | n/a | n/a | OUT: not in M3 scope (Scope Freeze v1.0) | Not Met: the release is one deployable, so the scale-out and data-ownership checks cannot pass | NOT IMPLEMENTED (accepted debt: CR-014, TD-01)