## Change Register
Controlled changes raised against the M1 baseline
CR ID | Affects | Requested change | Status | Owner
CR-001 | NFR-002 | Confirm feedback latency as 15 s; correct the M1 'Z sec' wording. | Open | M. Malope
CR-002 | NFR-004 | Confirm 3 s at 1,000 seeded requests; record the seeding method. | Open | M. Malope
CR-003 | NFR-006, FR-020, D-004 | Close the authentication and authorisation decision. | Open | G. Enright
CR-004 | FR-011 (AC-011.2) | Confirm reassignment rules for an already-owned request. | Open | M. Malope with ST-2
CR-005 | FR-016 (AC-016.2) | Add a target-response field so 'overdue' is definable. | Open | M. Malope raises, K. Marota implements
CR-006 | FR-018 (AC-018.2) | Decide whether reporting export is in scope or deferred. | Open | M. Malope with ST-3 and ST-5
CR-007 | FR-023 | Confirm sponsor view: dedicated or reuse management reporting. | Open | M. Malope with ST-5
CR-008 | FR-002, FR-021 | Confirm the initial controlled category list content. | Open | M. Malope with ST-3
CR-009 | FR-007 (AC-007.2), FR-012 (AC-012.1) | Introduce Rejected as a terminal status that can only be reached from Received and always carries a reason. | Proposed | K. Marota proposes, M. Malope records
CR-010 | ADR-001 (superseded, D-005); RTM architecture and data columns; ADR-002, ADR-004 to ADR-007 | Move from the modular monolith to four services (Requests, Access, ReferenceData, Reporting) behind one API entry point, with a schema per service in one PostgreSQL instance, so the system can grow without a redesign. Functional scope stays the same. | Approved through the revised ADR-001 (D-005) | K. Marota (architecture), M. Malope (requirements impact)
CR-011 | NFR-010 (new), ASR-05 (restated), ASR-07 (new), conflict C-5 (new) | Introduce NFR-010 Growth Readiness with three checks and no volume target; restate ASR-05; add ASR-07 and C-5. | Open | M. Malope
EC-001 | FR-021 (AC-021.1) | Editorial correction: AC-021.1 cited AC-002.3, which does not exist; it now cites AC-002.1. No change in meaning. | Applied | M. Malope