## Change Register
Controlled changes raised against the M1 baseline - M3 settlement (v3.0)
CR ID | Affects | Requested change | Status | Owner | M3 Decision | M3 Evidence / Reason | Decided (status, date, by)
CR-001 | NFR-002 | Confirm feedback latency as 15 s; correct the M1 'Z sec' wording. | Open | M. Malope | Approved and applied | PED v3 NFR-002 reads 15 s. NFR-002 is now built (5 s polling) and verified by UpdatesPollingTests (CR-016). | Proposed for the scope freeze meeting, 2026-10-12, M. Malope
CR-002 | NFR-004 | Confirm 3 s at 1,000 seeded requests; record the seeding method. | Open | M. Malope | Approved | Target stays 3 s at 1,000 requests. PT-01 seeds 1,000 requests through the API (Test/Performance/PT-01_queue.sh) and passed: p95 0.064 s with 5 users (Test/Evidence/PT-01_Results.md). Measured locally; staging pending (B2). | Proposed for the scope freeze meeting, 2026-10-12, M. Malope
CR-003 | NFR-006, FR-020, D-004 | Close the authentication and authorisation decision. | Open | G. Enright | Deferred to M4 | M3 runs on the development identity, which Program.cs allows only in Development. Residual risk RSK-012. Blocks staging (B2) until closed. AC-019.1 and AC-020.1 are verified against the development sign-in only. | Proposed, needs G. Enright, 2026-10-12, M. Malope
CR-004 | FR-011 (AC-011.2) | Confirm reassignment rules for an already-owned request. | Open | M. Malope with ST-2 | Approved: an owned request cannot be taken; no reassignment in M3 | Conditional update returns 409 / AlreadyOwned. Evidence: UT-03 4/4, IT-02 passed locally, AC-011.2 UI check passed (Test/Evidence/M3_Acceptance_Checks.md). Authorised reassignment is deferred. | Proposed for the scope freeze meeting, 2026-10-12, M. Malope
CR-005 | FR-016 (AC-016.2) | Add a target-response field so 'overdue' is definable. | Open | M. Malope raises, K. Marota implements | Approved and implemented: each category has a target response time in hours (default 72, set by administrators); a request's due time is fixed when it is submitted | Built in the release candidate (TargetResponseAtUtc, migration AddRemainingRequirements). Evidence: ResponseTargetTests, CategoryServiceTests, ReportingTests (AC-016.2) pass, 16 Oct 2026. | Decided 2026-10-14, M. Malope; for team sign-off with CR-016
CR-006 | FR-018 (AC-018.2) | Decide whether reporting export is in scope or deferred. | Open | M. Malope with ST-3 and ST-5 | Approved and implemented: CSV export of the performance table and of the matching requests, with the same filters as the page | The export matches the display row for row (ReportingTests, AC-018.2), 16 Oct 2026. | Decided 2026-10-14, M. Malope; for team sign-off with CR-016
CR-007 | FR-023 | Confirm sponsor view: dedicated or reuse management reporting. | Open | M. Malope with ST-5 | Approved and implemented: a Sponsor role with its own summary page that reuses the management figures at summary level | Pages/Reports/Summary; sponsors see no request details (ReportingTests AC-023.1, RequestAccessTests), 16 Oct 2026. Adds a fifth role, Sponsor, to the roles in ADR-005. | Decided 2026-10-14, M. Malope; for team sign-off with CR-016
CR-008 | FR-002, FR-021 | Confirm the initial controlled category list content. | Open | M. Malope with ST-3 | Approved | Initial list: Fault, Equipment, Security, IT, Maintenance, Lost Property, Other (AC-002.1). Held as reference data (Category) and seeded (DevelopmentSeed). Maintenance by administrators (FR-021) is built (CR-016). | Proposed for the scope freeze meeting, 2026-10-12, M. Malope
CR-009 | FR-007 (AC-007.2), FR-012 (AC-012.1) | Introduce Rejected as a terminal status that can only be reached from Received and always carries a reason. | Proposed | K. Marota proposes, M. Malope records | Approved and implemented: Rejected is terminal, reachable only from Received, and always carries a reason the requester sees | RequestStatus.Rejected, StatusTransition, StatusTransitionService.RejectAsync; database check constraints widened (migration AddRemainingRequirements). Evidence: StatusTransitionTests, StatusTransitionServiceTests (AC-007.2), UpdatesPollingTests pass, 16 Oct 2026. | Decided 2026-10-14, M. Malope; for team sign-off with CR-016
CR-010 | ADR-001 (superseded, D-005); RTM architecture and data columns; ADR-002, ADR-004 to ADR-007 | Move from the modular monolith to four services (Requests, Access, ReferenceData, Reporting) behind one API entry point, with a schema per service in one PostgreSQL instance, so the system can grow without a redesign. Functional scope stays the same. | Approved through the revised ADR-001 (D-005) | K. Marota (architecture), M. Malope (requirements impact) | Approved; not implemented in the M3 RC | The RC is one deployable (see CR-014). Code stays marked Changed (CR-010) in the RTM. | Unchanged, 2026-10-12, M. Malope
CR-011 | NFR-010 (new), ASR-05 (restated), ASR-07 (new), conflict C-5 (new) | Introduce NFR-010 Growth Readiness with three checks and no volume target; restate ASR-05; add ASR-07 and C-5. | Open | M. Malope | Approved and applied | NFR-010, ASR-05, ASR-07 and C-5 are in PED v3 on RTM-and-ASR-version-changes (pending merge). The NFR-010 checks are not run in M3 because the RC is one deployable. | Proposed for the scope freeze meeting, 2026-10-12, M. Malope
EC-001 | FR-021 (AC-021.1) | Editorial correction: AC-021.1 cited AC-002.3, which does not exist; it now cites AC-002.1. No change in meaning. | Applied | M. Malope | Applied | No change. | Unchanged
CR-012 | FR-014 (AC-014.2); ADR-005; Test Plan UT-04 seed | Reword AC-014.2: "Given a staff member who does not own the request or whose category scope does not cover it, and who is not an administrator, when they attempt to close, then the action is blocked (RBAC)." There is no separate close permission. | Proposed | M. Malope | Approve | Built rule: the owning, in-scope staff member or an administrator may close (AuthorisationPolicy). IT-03 and AuthorisationTests pass; administrator close passes in acceptance. Closes scope freeze B4. | Proposed for the scope freeze meeting, 2026-10-13, M. Malope
CR-013 | FR-015, FR-016, FR-017, FR-019, FR-020, FR-021 | Defer these Must requirements from the M3 release candidate to M4. Priority stays Must; no requirement is removed. | Withdrawn | M. Malope | Withdrawn: superseded by CR-016 | Every requirement it deferred (FR-015, FR-016, FR-017, FR-019, FR-020, FR-021) was built and verified before the release candidate, so nothing is deferred to M4. | Withdrawn 2026-10-16, M. Malope
CR-014 | ADR-001 (amended M3); ADR-004; CR-010; NFR-010 | Record that the M3 release candidate runs as one deployable: the web pages and the API share one application, not a separate frontend calling the Requests service. The pages already go through Application services and the queue repository. | Raised | K. Marota | Decide: technical debt for M4, or split before the RC | Found while building FR-008 and rechecked after the merge with main. Requirements are unaffected; the deviation is architectural. | Raised for K. Marota to decide, 2026-10-13, M. Malope
CR-015 | ADR-006; Docs/API/openapi.yaml; FR-012; FR-002 | Align the ADR-006 contract with the built API: status changes use POST /api/v1/requests/{id}/status (the contract says PATCH), and category ids are GUIDs (the contract says integers). | Raised | K. Marota | Decide: update ADR-006 and openapi.yaml, or change the API | The team accepted the POST route with the merged backend work; the GUID ids come from the data model. The API tests (IT-01, IT-03, ApiTests) use the built contract. | Raised for K. Marota to decide, 2026-10-13, M. Malope
CR-016 | FR-005, FR-006, FR-015 to FR-023, NFR-002, NFR-007, NFR-008; supersedes CR-013; Scope Freeze v2.0 | Bring the work built after the scope freeze into the M3 release candidate, so the release candidate's scope is what was built and verified. Priorities and acceptance criteria are unchanged. | Proposed | M. Malope | Approve | All these requirements are built with automated tests: 211/211 pass locally on 16 Oct 2026 (RTM v3.0 shows each test). Limits: real sign-in is CR-003, so AC-019.1 and AC-020.1 are verified against the development sign-in only; nothing is deployed yet (B2). | Proposed for team sign-off, 2026-10-16, M. Malope