## RTM
CivicConnect Requirements Traceability Matrix (RTM) - M1 baseline (live artefact, update every milestone)
Req ID | Requirement | Source (Stakeholder) | Priority | Acceptance Criteria | Design / Architecture (→ M2) | Issue / PR (→ M3) | Implementation (→ M3) | Test / Verification (→ M3) | Acceptance / Release Evidence (→ M4) | Status | Owner
FR-001 | Submit a new service request with the information needed to action it. | ST-1 | Must | AC-001.1; AC-001.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-002 | Categorise the request from a controlled category list (not free text). | ST-1, ST-3 | Must | AC-002.1; AC-002.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-003 | View the current status of a submitted request. | ST-1 | Must | AC-003.1; AC-003.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-004 | View a history/list of own previously submitted requests. | ST-1 | Must | AC-004.1; AC-004.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-005 | Search/filter own request history. | ST-1 | Should | AC-005.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-006 | Attach supporting information to a request (e.g. a photo). | ST-1, ST-2 | Could | AC-006.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate — may defer
FR-007 | Receive feedback when a request is accepted, rejected, updated or completed. | ST-1 | Must | AC-007.1; AC-007.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-008 | View the service requests relevant to authorised staff (staff queue). | ST-2 | Must | AC-008.1; AC-008.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-009 | Search, filter or sort requests using useful criteria. | ST-2 | Must | AC-009.1; AC-009.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-010 | View the full details of a request. | ST-2 | Must | AC-010.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-011 | Assign or accept responsibility for a request. | ST-2 | Must | AC-011.1; AC-011.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-012 | Update a request's status through controlled transitions. | ST-2 | Must | AC-012.1; AC-012.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-013 | Record actions, comments or resolution information on a request. | ST-2 | Must | AC-013.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-014 | Resolve or close requests where authorised. | ST-2 | Must | AC-014.1; AC-014.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-015 | View useful service-activity information (oversight overview). | ST-3 | Must | AC-015.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-016 | Identify open, overdue, resolved and closed requests. | ST-3 | Must | AC-016.1; AC-016.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-017 | View request information by category/status (or another justified dimension). | ST-3 | Must | AC-017.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-018 | Access enough information to support accountability and service-performance analysis. | ST-3 | Should | AC-018.1; AC-018.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-019 | Manage user accounts. | ST-4 | Must | AC-019.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-020 | Manage roles and permissions (RBAC). | ST-4 | Must | AC-020.1; AC-020.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-021 | Maintain the controlled category list. | ST-4 | Must | AC-021.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-022 | Access an audit trail of key controlled actions. | ST-4 | Should | AC-022.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
FR-023 | Access high-level service-performance and accountability reporting. | ST-5 | Should | AC-023.1 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
NFR-001 | Usability: a first-time requester can submit in ≤ 5 steps / 5 min. | ST-1 | Should | ≤ 5 steps and ≤ 5 min (usability test) | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
NFR-002 | Feedback timeliness: a change is visible to the requester within 15 s. | ST-1 | Should | ≤ 15 s after a staff status change (measured) | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
NFR-003 | Privacy: a requester can never view another requester's request. | ST-1 | Must | Access-control test; supports AC-004.2 | → M2 | → M3 | → M3 | → M3 | → M4 | Baseline candidate
NFR-004 | Performance: staff queue and oversight views load quickly under load. | ST-2, ST-3 | Should | ≤ 3 s for 1,000 requests (confirm target) | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate
NFR-005 | Concurrency & integrity: no double-ownership or lost updates. | ST-2 | Must | No two owners; atomic transitions (supports FR-011/012) | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate
NFR-006 | Security / RBAC: every action authorised by role. | ST-4 | Must | Unauthorised access denied (supports FR-008/014/020) | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate
NFR-007 | Auditability: key actions recorded and tamper-evident. | ST-4 | Must | Actor+timestamp, not silently altered (supports FR-013/022) | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate
NFR-008 | Reporting accuracy: reports reconcile with the underlying records. | ST-3, ST-5 | Should | No discrepancy between report and data | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate
NFR-009 | Cost sustainability: run within free/low-cost tiers where practical. | ST-5 | Should | Runs within free/low-cost tiers; cost documented | → M2 | → M3 | → M3 | → M3 | → M4 | Candidate

## Legend & How-to
CivicConnect RTM — How to use this workbook
Purpose | Traces every requirement from its stakeholder source through to release evidence. LIVE artefact — update it whenever a requirement, design, PR, test or release changes. Do not silently edit a baselined requirement; change it through change control and update this matrix.
You fill in | The shaded (yellow) forward columns — Design/Architecture (M2), Issue/PR, Implementation, Test/Verification (M3), Acceptance/Release Evidence (M4) — as that evidence is produced. Replace the "→ M2/M3/M4" placeholders with real references (e.g. ADR-003, PR #14, SubmitForm, TEST-012, release v1.0).
M1 scope | Only Source → Requirement → Acceptance Criteria is populated now. Correct for M1. For the defence, trace ONE requirement (e.g. FR-001 or FR-003) across its row and explain what evidence is still pending.
IDs are stable | Never renumber FR/NFR/AC IDs after baseline. New requirements get the next free number.
Cross-reference | Requirement wording and acceptance criteria live in the requirements documents (Requester, and Staff/Management/Administrator/Sponsor); this matrix references them by ID.
Traceability chain (target by M4)
Chain | Stakeholder/Source → Requirement (FR/NFR) → Acceptance Criteria → Design/Architecture → Issue/PR → Implementation → Test → Acceptance/Release Evidence
Stakeholder source IDs
ST-1 | Requester (primary user of these requirements)
ST-2 | Service Staff
ST-3 | Management / Oversight
ST-4 | System Administrator
ST-5 | Sponsor (the organisation)
Priority (MoSCoW)
Must | Required for the baseline release
Should | Important but not vital
Could | Desirable; first to drop under pressure
Won't | Explicitly out of scope this release
Status values
Baseline candidate | Drafted; proposed for M1 baseline sign-off
Baselined | Approved and under change control
Candidate — may defer | Under discussion; deferment possible (record rationale in Decision Log)
Candidate | Not yet baseline-ready; needs a target or an M2 decision
Deferred | Moved to future scope